## A-Setup
Quarterly Project Portfolio Dashboard
Purpose
Forecast the monthly allocation by project
Tab Description
A-Setup | This tab containing instructions and description
1-QrtrDashboard | Quarterly dashboard on project portfolio
(1-PivotsQrtrDashboard) | Hidden pivots for the quarterly dashboard
2-ResourceForecast | Yearly and monthly Allocation (FTE) per role
(2-RFcstPivots) | Hidden pivot for the yearly allocation (FTE) per role
Power Queries
1-Load | Loaded data
Portfolio | /* Load Portfolio */
Dimensions: Project Type Region Department Complexity Status Phase | /* Load dimension tables */
LOE Hours | /* Load average LOE hours */
AssumedDuration | /* Load average duration per phase per project type */
2-Transform | Transformations
Portfolio_Forecast | /* Calculation of start dates per phase */
Forecast_Phase1 | /* Calculate monthlz allocation for Phase 1 */
Forecast_Phase2 | /* Calculate monthlz allocation for Phase 2 */
Forecast_Phase3 | /* Calculate monthlz allocation for Phase 3 */
Forecast_Phase4 | /* Calculate monthlz allocation for Phase 4 */
Forecast_Phase5 | /* Calculate monthlz allocation for Phase 5 */
3-Load | /* Main table */
Forecast_AllPhases
fnPeriod | Function for monthly allocation calculation
fnPeriod | Function for monthly allocation calculation
References
1 | https://www.youtube.com/watch?v=O3AnAKjRBLM
Automate Allocation of Amounts Across Months Using Power Query in Excel
ExcelFort
2 | https://www.youtube.com/watch?v=arEs1K6TijI
Project Management Dataset for Power BI ¦ Community ¦ Free Dataset #2
Ariel Lomoctos
3 | https://www.youtube.com/watch?v=vjBprojOCzU
Power BI Tutorial ¦ From Flat File To Data Model
Guy in a Cube
4 | Thinking Like An Analyst course
Maven Analytics
Versions
V2 | Main query Forecast_AllPhases is pushed to the Data Model Charts' source are from data model instead of query Forecast_AllPhases
V1 | Initial version
NOTE TO SELF: FILTER FROM 1 to many table

## 1-PivotsQrtrDashboard (hidden)
Total Projects in Progress, Costs, Benefits
Status | In - Progress
Count of ID | Sum of Project Cost | Sum of Project Benefit
13 | 56433536 | 114886985
Projects in Progress by Phase
Status | In - Progress
Row Labels | Count of ID
Phase 1 - Explore | 2
Phase 2 - Develop | 3
Phase 3 - Plan | 4
Phase 4 - Implement | 4
Grand Total | 13
Capacity per Project Manager |  |  |  | BA Capacity
Role | Project Manager |  |  | Role | Business Analyst
Row Labels | Sum of Monthly Allocation FTE |  |  | Row Labels | Sum of Monthly Allocation FTE
2023 |  |  |  | 2023
Qtr1 |  |  |  | Qtr1
Jan |  |  |  | Jan | 0.37784
Brenda Chandler | 0.2339 |  |  | Feb | 0.49763
Deacon Delacruz | 0.11742 |  |  | Mar | 0.48722
Kamari Norris | 0.31155 |  |  | Grand Total | 1.3627
Feb
Brenda Chandler | 0.23295
Deacon Delacruz | 0.13163
Kamari Norris | 0.23864
Mar
Brenda Chandler | 0.17614
Deacon Delacruz | 0.088068
Kamari Norris | 0.14678
Grand Total | 1.6771
Realized Benefits in 2022 (Project End Date 2022) |  |  |  | Realized Benefits in 2021 (Project End Date 2021)
Status | Completed |  |  | Status | Completed
End Date | (Multiple Items) |  |  | End Date | (Multiple Items)
Sum of Project Benefit |  |  |  | Sum of Project Benefit
123500841 |  |  |  | 96923698
Realized Benefits in Q4 2022 (Project End Date Q4 2022) |  |  |  | Realized Benefits in Q3 2022 (Project End Date Q3 2022)
Status | Completed |  |  | Status | Completed
Sum of Project Benefit |  |  |  | Sum of Project Benefit
52372304 |  |  |  | 35563157
Status | Completed
Sum of Project Benefit | Column Labels
Row Labels | 2021 | 2022 | Grand Total
Qtr1
Jan |  | 18067955 | 18067955
Mar |  | 8802862 | 8802862
Qtr2
Jun | 34656691 | 8694563 | 43351254
Qtr3
Jul | 17689061 | 26551519 | 44240580
Aug | 18143348 | 9011638 | 27154986
Qtr4
Oct | 9125362 | 26223425 | 35348787
Nov | 8547257 | 26148879 | 34696136
Dec | 8761979 |  | 8761979
Grand Total | 96923698 | 123500841 | 220424539
Forecasted Benefits in Q1 2023 (Project Target End Date Q1 2022)
Status | In - Progress
Sum of Project Benefit
88495917
Top 5 Projects Benefits Next Period
Status | In - Progress
Start Date | (Multiple Items)
Row Labels | Sum of Project Benefit
Coding Region | 9127150
Evening Shindig | 9084736
Leadership Minds | 9040473
School Leadership 2.0 | 9022111
Road-To-Success Workshop | 9006076
Top 5 Projects Costs Next Period
Status | In - Progress
Start Date | (Multiple Items)
Row Labels | Sum of Project Cost
The Code Honors | 5896885
The Experienced Dude | 5570834
Mentee To Mentor | 5072095
The Morning Ceremony | 4802423
Road-To-Success Workshop | 4646988
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## 1-QrtrDashboard
Quarterly Project Portfolio Dashboard |  | Period: Q4 2022 | Region:
| This is the benefit we have realized… |  | The Project Managers are currently working on these projects… |  | This is the expected benefit for the next period…
| 123500841 | 47.27% | 13 | 56433536 | 88495917
|  | QoQ |  | Portfolio Cost
|  | 27.42% |  | 114886985
| Total Quarterly Benefit | YoY |  | Portfolio Benefits | Upcoming Benefit
| … and the trend in 2022 vs 2021 |  | … at this FTE rate in the next quarter. |  | … where these 5 projects will drive benefist and costs.
[5 empty] | Project Name | Benefit
[5 empty] | Coding Region | 9127150
[5 empty] | Evening Shindig | 9084736
[5 empty] | Leadership Minds | 9040473
[5 empty] | School Leadership 2.0 | 9022111
[5 empty] | Road-To-Success Workshop | 9006076
[5 empty] | Project Name | Cost
[5 empty] | The Code Honors | 5896885
[5 empty] | The Experienced Dude | 5570834
[5 empty] | Mentee To Mentor | 5072095
[5 empty] | The Morning Ceremony | 4802423
[5 empty] | Road-To-Success Workshop | 4646988
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## 2-RFcstPivots (hidden)
Resource Forecast - Yearly Allocation in FTE
Sum of Yearly Allocation FTE | Column Labels
Row Labels | Business Analyst | Project Manager | Grand Total
2020 | 0.10997 | 0.12993 | 0.2399
2021 | 0.81558 | 0.98374 | 1.7993
2022 | 1.048 | 1.1755 | 2.2236
2023 | 0.62753 | 0.75505 | 1.3826
2024 | 0.62125 | 0.74657 | 1.3678
2025 | 0.56207 | 0.57501 | 1.1371
2026 | 0.0093119 | 0.018624 | 0.027936
Grand Total | 3.7937 | 4.3845 | 8.1782

## 2-ResourceForecast
Resource Forecast
Yearly Allocation in FTE
Monthly Allocation in FTE
Project Duration Dates:
Sum of Monthly Allocation FTE | Column Labels
| 2022 |  |  | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 |  | Grand Total
Row Labels | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Project27
Business Analyst | 2022 Oct: 0.1089; 2022 Nov: 0.2197; 2022 Dec: 0.070076; 2023 Jan: 0.030303 | 0.42898
Project Manager | 2022 Oct: 0.17045; 2022 Nov: 0.22348; 2022 Dec: 0.125; 2023 Jan: 0.060606 | 0.57955
Project34
Business Analyst | 2022 Oct: 0.014678; 2022 Nov: 0.014205; 2022 Dec: 0.014678 | 0.043561
Project Manager | 2022 Oct: 0.044034; 2022 Nov: 0.028883; 2022 Dec: 0.029356 | 0.10227
Project39
Business Analyst | 2022 Oct: 0.030303 | 0.030303
Project Manager | 2022 Oct: 0.060606 | 0.060606
Project40
Business Analyst | 2022 Oct: 0.014678 | 0.014678
Project Manager | 2022 Oct: 0.029356 | 0.029356
Project41
Business Analyst | 2022 Oct: 0.014678 | 0.014678
Project Manager | 2022 Oct: 0.029356 | 0.029356
Project42
Business Analyst | 2022 Oct: 0.014678; 2022 Nov: 0.014205 | 0.028883
Project Manager | 2022 Oct: 0.029356; 2022 Nov: 0.028409 | 0.057765
Project43
Business Analyst | 2022 Oct: 0.034091; 2022 Nov: 0.028409 | 0.0625
Project Manager | 2022 Oct: 0.060606; 2022 Nov: 0.056818 | 0.11742
Project44
Business Analyst | 2022 Oct: 0.014678; 2022 Nov: 0.014205; 2022 Dec: 0.014678 | 0.043561
Project Manager | 2022 Oct: 0.029356; 2022 Nov: 0.028409; 2022 Dec: 0.029356 | 0.087121
Project45
Business Analyst | 2022 Oct: 0.22727; 2022 Nov: 0.0625; 2022 Dec: 0.030303 | 0.32008
Project Manager | 2022 Oct: 0.23106; 2022 Nov: 0.11742; 2022 Dec: 0.060606 | 0.40909
Project46
Business Analyst | 2022 Oct: 0.028409; 2022 Nov: 0.17045; 2022 Dec: 0.17708; 2023 Jan: 0.029356; 2023 Feb: 0.026515 | 0.43182
Project Manager | 2022 Oct: 0.085227; 2022 Nov: 0.11364; 2022 Dec: 0.11932; 2023 Jan: 0.058712; 2023 Feb: 0.05303 | 0.42992
Project47
Business Analyst | 2022 Oct: 0.028409; 2022 Nov: 0.17045; 2022 Dec: 0.17708; 2023 Jan: 0.029356; 2023 Feb: 0.026515 | 0.43182
Project Manager | 2022 Oct: 0.085227; 2022 Nov: 0.11364; 2022 Dec: 0.11932; 2023 Jan: 0.058712; 2023 Feb: 0.05303 | 0.42992
Project48
Business Analyst | 2022 Oct: 0.028409; 2022 Nov: 0.11364; 2022 Dec: 0.23674; 2023 Jan: 0.056818; 2023 Feb: 0.026515 | 0.46212
Project Manager | 2022 Oct: 0.11364; 2022 Nov: 0.17045; 2022 Dec: 0.23864; 2023 Jan: 0.11364; 2023 Feb: 0.05303 | 0.68939
Project49
Business Analyst | 2022 Oct: 0.028409; 2022 Nov: 0.17045; 2022 Dec: 0.17708; 2023 Jan: 0.029356; 2023 Feb: 0.026515 | 0.43182
Project Manager | 2022 Oct: 0.085227; 2022 Nov: 0.11364; 2022 Dec: 0.11932; 2023 Jan: 0.058712; 2023 Feb: 0.05303 | 0.42992
Project50
Business Analyst | 2022 Oct: 0.11742; 2022 Nov: 0.014205; 2022 Dec: 0.014678; 2023 Jan: 0.014678; 2023 Feb: 0.013258 | 0.17424
Project Manager | 2022 Oct: 0.088068; 2022 Nov: 0.028409; 2022 Dec: 0.029356; 2023 Jan: 0.029356; 2023 Feb: 0.026515 | 0.2017
Project51
Business Analyst | 2022 Oct: 0.11742; 2022 Nov: 0.11364; 2022 Dec: 0.11742; 2023 Jan: 0.014678; 2023 Feb: 0.013258; 2023 Mar: 0.014678; 2023 Apr: 0.014205 | 0.4053
Project Manager | 2022 Oct: 0.058712; 2022 Nov: 0.08428; 2022 Dec: 0.088068; 2023 Jan: 0.029356; 2023 Feb: 0.026515; 2023 Mar: 0.029356; 2023 Apr: 0.028409 | 0.3447
Project52
Business Analyst | 2023 Jan: 0.028409; 2023 Feb: 0.15909; 2023 Mar: 0.17614; 2023 Apr: 0.033144; 2023 May: 0.029356 | 0.42614
Project Manager | 2023 Jan: 0.085227; 2023 Feb: 0.10606; 2023 Mar: 0.11742; 2023 Apr: 0.058712; 2023 May: 0.058712 | 0.42614
Project53
Business Analyst | 2022 Oct: 0.012784; 2022 Nov: 0.014205; 2022 Dec: 0.10748; 2023 Jan: 0.11742; 2023 Feb: 0.10606; 2023 Mar: 0.11742; 2023 Apr: 0.020833; 2023 May: 0.014678; 2023 Jun: 0.014205; 2023 Jul: 0.014678 | 0.53977
Project Manager | 2022 Oct: 0.038352; 2022 Nov: 0.042614; 2022 Dec: 0.057292; 2023 Jan: 0.058712; 2023 Feb: 0.078598; 2023 Mar: 0.088068; 2023 Apr: 0.032197; 2023 May: 0.029356; 2023 Jun: 0.028409; 2023 Jul: 0.029356 | 0.48295
Project54
Business Analyst | 2022 Dec: 0.012784; 2023 Jan: 0.014678; 2023 Feb: 0.074811; 2023 Mar: 0.088068; 2023 Apr: 0.085227; 2023 May: 0.088068; 2023 Jun: 0.018939; 2023 Jul: 0.014678; 2023 Aug: 0.014678; 2023 Sep: 0.014205 | 0.42614
Project Manager | 2022 Dec: 0.051136; 2023 Jan: 0.058712; 2023 Feb: 0.05303; 2023 Mar: 0.058712; 2023 Apr: 0.069602; 2023 May: 0.07339; 2023 Jun: 0.044508; 2023 Jul: 0.044034; 2023 Aug: 0.02983; 2023 Sep: 0.028409 | 0.51136
Project55
Business Analyst | 2022 Oct: 0.014678; 2022 Nov: 0.014205; 2022 Dec: 0.014678 | 0.043561
Project Manager | 2022 Oct: 0.029356; 2022 Nov: 0.028409; 2022 Dec: 0.029356 | 0.087121
Project56
Business Analyst | 2023 May: 0.026515; 2023 Jun: 0.10795; 2023 Jul: 0.22727; 2023 Aug: 0.064394; 2023 Sep: 0.028409 | 0.45455
Project Manager | 2023 May: 0.10606; 2023 Jun: 0.16667; 2023 Jul: 0.23106; 2023 Aug: 0.12121; 2023 Sep: 0.056818 | 0.68182
Project57
Business Analyst | 2023 Jan: 0.012784; 2023 Feb: 0.013258; 2023 Mar: 0.076231; 2023 Apr: 0.085227; 2023 May: 0.088068; 2023 Jun: 0.085227; 2023 Jul: 0.02178; 2023 Aug: 0.014678; 2023 Sep: 0.014205; 2023 Oct: 0.014678 | 0.42614
Project Manager | 2023 Jan: 0.051136; 2023 Feb: 0.05303; 2023 Mar: 0.058712; 2023 Apr: 0.056818; 2023 May: 0.071496; 2023 Jun: 0.071023; 2023 Jul: 0.046875; 2023 Aug: 0.044034; 2023 Sep: 0.028883; 2023 Oct: 0.029356 | 0.51136
Project58
Business Analyst | 2023 Jun: 0.025568; 2023 Jul: 0.16193; 2023 Aug: 0.17614; 2023 Sep: 0.033144; 2023 Oct: 0.029356 | 0.42614
Project Manager | 2023 Jun: 0.076705; 2023 Jul: 0.11458; 2023 Aug: 0.11742; 2023 Sep: 0.058712; 2023 Oct: 0.058712 | 0.42614
Project59
Business Analyst | 2023 Jul: 0.026515; 2023 Aug: 0.11174; 2023 Sep: 0.22348; 2023 Oct: 0.064394; 2023 Nov: 0.028409 | 0.45455
Project Manager | 2023 Jul: 0.10606; 2023 Aug: 0.17235; 2023 Sep: 0.22538; 2023 Oct: 0.12121; 2023 Nov: 0.056818 | 0.68182
Project60
Business Analyst | 2023 Jul: 0.026515; 2023 Aug: 0.11174; 2023 Sep: 0.22348; 2023 Oct: 0.064394; 2023 Nov: 0.028409 | 0.45455
Project Manager | 2023 Jul: 0.10606; 2023 Aug: 0.17235; 2023 Sep: 0.22538; 2023 Oct: 0.12121; 2023 Nov: 0.056818 | 0.68182
Project61
Business Analyst | 2023 Jul: 0.026515; 2023 Aug: 0.11174; 2023 Sep: 0.22348; 2023 Oct: 0.064394; 2023 Nov: 0.028409 | 0.45455
Project Manager | 2023 Jul: 0.10606; 2023 Aug: 0.17235; 2023 Sep: 0.22538; 2023 Oct: 0.12121; 2023 Nov: 0.056818 | 0.68182
Project62
Business Analyst | 2023 Feb: 0.011837; 2023 Mar: 0.014678; 2023 Apr: 0.075758; 2023 May: 0.088068; 2023 Jun: 0.085227; 2023 Jul: 0.088068; 2023 Aug: 0.019413; 2023 Sep: 0.014205; 2023 Oct: 0.014678; 2023 Nov: 0.014205 | 0.42614
Project Manager | 2023 Feb: 0.047348; 2023 Mar: 0.058712; 2023 Apr: 0.056818; 2023 May: 0.058712; 2023 Jun: 0.069602; 2023 Jul: 0.07339; 2023 Aug: 0.045928; 2023 Sep: 0.042614; 2023 Oct: 0.02983; 2023 Nov: 0.028409 | 0.51136
Project63
Business Analyst | 2023 Sep: 0.025568; 2023 Oct: 0.16193; 2023 Nov: 0.17045; 2023 Dec: 0.038826; 2024 Jan: 0.029356 | 0.42614
Project Manager | 2023 Sep: 0.076705; 2023 Oct: 0.11458; 2023 Nov: 0.11364; 2023 Dec: 0.0625; 2024 Jan: 0.058712 | 0.42614
Project64
Business Analyst | 2023 Sep: 0.025568; 2023 Oct: 0.1089; 2023 Nov: 0.2197; 2023 Dec: 0.070076; 2024 Jan: 0.030303 | 0.45455
Project Manager | 2023 Sep: 0.10227; 2023 Oct: 0.17045; 2023 Nov: 0.22348; 2023 Dec: 0.125; 2024 Jan: 0.060606 | 0.68182
Project65
Business Analyst | 2023 Apr: 0.011364; 2023 May: 0.014678; 2023 Jun: 0.097064; 2023 Jul: 0.11742; 2023 Aug: 0.11742; 2023 Sep: 0.11364; 2023 Oct: 0.024621; 2023 Nov: 0.014205; 2023 Dec: 0.014678; 2024 Jan: 0.014678 | 0.53977
Project Manager | 2023 Apr: 0.034091; 2023 May: 0.044034; 2023 Jun: 0.054451; 2023 Jul: 0.058712; 2023 Aug: 0.08428; 2023 Sep: 0.085227; 2023 Oct: 0.035038; 2023 Nov: 0.028409; 2023 Dec: 0.029356; 2024 Jan: 0.029356 | 0.48295
Project66
Business Analyst | 2023 Apr: 0.011364; 2023 May: 0.014678; 2023 Jun: 0.07339; 2023 Jul: 0.088068; 2023 Aug: 0.088068; 2023 Sep: 0.085227; 2023 Oct: 0.02178; 2023 Nov: 0.014205; 2023 Dec: 0.014678; 2024 Jan: 0.014678 | 0.42614
Project Manager | 2023 Apr: 0.045455; 2023 May: 0.058712; 2023 Jun: 0.056818; 2023 Jul: 0.058712; 2023 Aug: 0.071496; 2023 Sep: 0.071023; 2023 Oct: 0.046875; 2023 Nov: 0.042614; 2023 Dec: 0.030303; 2024 Jan: 0.029356 | 0.51136
Project67
Business Analyst | 2023 May: 0.012311; 2023 Jun: 0.014205; 2023 Jul: 0.10417; 2023 Aug: 0.11742; 2023 Sep: 0.11364; 2023 Oct: 0.11742; 2023 Nov: 0.017519; 2023 Dec: 0.014678; 2024 Jan: 0.014678; 2024 Feb: 0.013731 | 0.53977
Project Manager | 2023 May: 0.036932; 2023 Jun: 0.042614; 2023 Jul: 0.056818; 2023 Aug: 0.058712; 2023 Sep: 0.083333; 2023 Oct: 0.088068; 2023 Nov: 0.030303; 2023 Dec: 0.029356; 2024 Jan: 0.029356; 2024 Feb: 0.027462 | 0.48295
Project68
Business Analyst | 2023 Dec: 0.027462; 2024 Jan: 0.1714; 2024 Feb: 0.16477; 2024 Mar: 0.034091; 2024 Apr: 0.028409 | 0.42614
Project Manager | 2023 Dec: 0.082386; 2024 Jan: 0.11648; 2024 Feb: 0.10985; 2024 Mar: 0.060606; 2024 Apr: 0.056818 | 0.42614
Project69
Business Analyst | 2023 Aug: 0.012311; 2023 Sep: 0.014205; 2023 Oct: 0.078598; 2023 Nov: 0.085227; 2023 Dec: 0.088068; 2024 Jan: 0.088068; 2024 Feb: 0.016098; 2024 Mar: 0.014678; 2024 Apr: 0.014205; 2024 May: 0.014678 | 0.42614
Project Manager | 2023 Aug: 0.049242; 2023 Sep: 0.056818; 2023 Oct: 0.058712; 2023 Nov: 0.056818; 2023 Dec: 0.07197; 2024 Jan: 0.07339; 2024 Feb: 0.04214; 2024 Mar: 0.044034; 2024 Apr: 0.028883; 2024 May: 0.029356 | 0.51136
Project70
Business Analyst | 2023 Sep: 0.012311; 2023 Oct: 0.014678; 2023 Nov: 0.10369; 2023 Dec: 0.11742; 2024 Jan: 0.11742; 2024 Feb: 0.10985; 2024 Mar: 0.021307; 2024 Apr: 0.014205; 2024 May: 0.014678; 2024 Jun: 0.014205 | 0.53977
Project Manager | 2023 Sep: 0.036932; 2023 Oct: 0.044034; 2023 Nov: 0.055398; 2023 Dec: 0.058712; 2024 Jan: 0.086174; 2024 Feb: 0.082386; 2024 Mar: 0.033144; 2024 Apr: 0.028409; 2024 May: 0.029356; 2024 Jun: 0.028409 | 0.48295
Project71
Business Analyst | 2024 May: 0.026515; 2024 Jun: 0.16098; 2024 Jul: 0.17614; 2024 Aug: 0.034091; 2024 Sep: 0.028409 | 0.42614
Project Manager | 2024 May: 0.079545; 2024 Jun: 0.11174; 2024 Jul: 0.11742; 2024 Aug: 0.060606; 2024 Sep: 0.056818 | 0.42614
Project72
Business Analyst | 2024 Jun: 0.025568; 2024 Jul: 0.16193; 2024 Aug: 0.17614; 2024 Sep: 0.033144; 2024 Oct: 0.029356 | 0.42614
Project Manager | 2024 Jun: 0.076705; 2024 Jul: 0.11458; 2024 Aug: 0.11742; 2024 Sep: 0.058712; 2024 Oct: 0.058712 | 0.42614
Project73
Business Analyst | 2024 Jul: 0.026515; 2024 Aug: 0.11174; 2024 Sep: 0.22348; 2024 Oct: 0.064394; 2024 Nov: 0.028409 | 0.45455
Project Manager | 2024 Jul: 0.10606; 2024 Aug: 0.17235; 2024 Sep: 0.22538; 2024 Oct: 0.12121; 2024 Nov: 0.056818 | 0.68182
Project74
Business Analyst | 2024 Jul: 0.026515; 2024 Aug: 0.11174; 2024 Sep: 0.22348; 2024 Oct: 0.064394; 2024 Nov: 0.028409 | 0.45455
Project Manager | 2024 Jul: 0.10606; 2024 Aug: 0.17235; 2024 Sep: 0.22538; 2024 Oct: 0.12121; 2024 Nov: 0.056818 | 0.68182
Project75
Business Analyst | 2024 Aug: 0.026515; 2024 Sep: 0.10795; 2024 Oct: 0.22727; 2024 Nov: 0.0625; 2024 Dec: 0.030303 | 0.45455
Project Manager | 2024 Aug: 0.10606; 2024 Sep: 0.16667; 2024 Oct: 0.23106; 2024 Nov: 0.11742; 2024 Dec: 0.060606 | 0.68182
Project76
Business Analyst | 2024 Mar: 0.011837; 2024 Apr: 0.014205; 2024 May: 0.076231; 2024 Jun: 0.085227; 2024 Jul: 0.088068; 2024 Aug: 0.088068; 2024 Sep: 0.018939; 2024 Oct: 0.014678; 2024 Nov: 0.014205; 2024 Dec: 0.014678 | 0.42614
Project Manager | 2024 Mar: 0.047348; 2024 Apr: 0.056818; 2024 May: 0.058712; 2024 Jun: 0.056818; 2024 Jul: 0.071496; 2024 Aug: 0.07339; 2024 Sep: 0.044508; 2024 Oct: 0.044034; 2024 Nov: 0.028883; 2024 Dec: 0.029356 | 0.51136
Project77
Business Analyst | 2024 Aug: 0.026515; 2024 Sep: 0.16098; 2024 Oct: 0.17614; 2024 Nov: 0.033144; 2024 Dec: 0.029356 | 0.42614
Project Manager | 2024 Aug: 0.079545; 2024 Sep: 0.11174; 2024 Oct: 0.11742; 2024 Nov: 0.058712; 2024 Dec: 0.058712 | 0.42614
Project78
Business Analyst | 2024 Oct: 0.028409; 2024 Nov: 0.17045; 2024 Dec: 0.17708; 2025 Jan: 0.029356; 2025 Feb: 0.026515 | 0.43182
Project Manager | 2024 Oct: 0.085227; 2024 Nov: 0.11364; 2024 Dec: 0.11932; 2025 Jan: 0.058712; 2025 Feb: 0.05303 | 0.42992
Project79
Business Analyst | 2024 May: 0.012784; 2024 Jun: 0.014205; 2024 Jul: 0.080966; 2024 Aug: 0.088068; 2024 Sep: 0.085227; 2024 Oct: 0.088068; 2024 Nov: 0.014205; 2024 Dec: 0.014678; 2025 Jan: 0.014678; 2025 Feb: 0.013258 | 0.42614
Project Manager | 2024 May: 0.051136; 2024 Jun: 0.056818; 2024 Jul: 0.058712; 2024 Aug: 0.058712; 2024 Sep: 0.070549; 2024 Oct: 0.07339; 2024 Nov: 0.042614; 2024 Dec: 0.043561; 2025 Jan: 0.029356; 2025 Feb: 0.026515 | 0.51136
Project80
Business Analyst | 2024 May: 0.012784; 2024 Jun: 0.014205; 2024 Jul: 0.080966; 2024 Aug: 0.088068; 2024 Sep: 0.085227; 2024 Oct: 0.088068; 2024 Nov: 0.014205; 2024 Dec: 0.014678; 2025 Jan: 0.014678; 2025 Feb: 0.013258 | 0.42614
Project Manager | 2024 May: 0.051136; 2024 Jun: 0.056818; 2024 Jul: 0.058712; 2024 Aug: 0.058712; 2024 Sep: 0.070549; 2024 Oct: 0.07339; 2024 Nov: 0.042614; 2024 Dec: 0.043561; 2025 Jan: 0.029356; 2025 Feb: 0.026515 | 0.51136
Project81
Business Analyst | 2024 Oct: 0.028409; 2024 Nov: 0.11364; 2024 Dec: 0.23674; 2025 Jan: 0.056818; 2025 Feb: 0.026515 | 0.46212
Project Manager | 2024 Oct: 0.11364; 2024 Nov: 0.17045; 2024 Dec: 0.23864; 2025 Jan: 0.11364; 2025 Feb: 0.05303 | 0.68939
Project82
Business Analyst | 2024 May: 0.012784; 2024 Jun: 0.014205; 2024 Jul: 0.080966; 2024 Aug: 0.088068; 2024 Sep: 0.085227; 2024 Oct: 0.088068; 2024 Nov: 0.014205; 2024 Dec: 0.014678; 2025 Jan: 0.014678; 2025 Feb: 0.013258 | 0.42614
Project Manager | 2024 May: 0.051136; 2024 Jun: 0.056818; 2024 Jul: 0.058712; 2024 Aug: 0.058712; 2024 Sep: 0.070549; 2024 Oct: 0.07339; 2024 Nov: 0.042614; 2024 Dec: 0.043561; 2025 Jan: 0.029356; 2025 Feb: 0.026515 | 0.51136
Project83
Business Analyst | 2024 Oct: 0.028409; 2024 Nov: 0.11364; 2024 Dec: 0.23674; 2025 Jan: 0.056818; 2025 Feb: 0.026515 | 0.46212
Project Manager | 2024 Oct: 0.11364; 2024 Nov: 0.17045; 2024 Dec: 0.23864; 2025 Jan: 0.11364; 2025 Feb: 0.05303 | 0.68939
Project84
Business Analyst | 2024 Dec: 0.028409; 2025 Jan: 0.18182; 2025 Feb: 0.15909; 2025 Mar: 0.034091; 2025 Apr: 0.028409 | 0.43182
Project Manager | 2024 Dec: 0.085227; 2025 Jan: 0.12121; 2025 Feb: 0.10606; 2025 Mar: 0.060606; 2025 Apr: 0.056818 | 0.42992
Project85
Business Analyst | 2024 Jul: 0.012784; 2024 Aug: 0.014678; 2024 Sep: 0.080492; 2024 Oct: 0.088068; 2024 Nov: 0.085227; 2024 Dec: 0.088068; 2025 Jan: 0.014678; 2025 Feb: 0.013258; 2025 Mar: 0.014678; 2025 Apr: 0.014205 | 0.42614
Project Manager | 2024 Jul: 0.051136; 2024 Aug: 0.058712; 2024 Sep: 0.056818; 2024 Oct: 0.058712; 2024 Nov: 0.070549; 2024 Dec: 0.07339; 2025 Jan: 0.044034; 2025 Feb: 0.039773; 2025 Mar: 0.02983; 2025 Apr: 0.028409 | 0.51136
Project86
Business Analyst | 2024 Sep: 0.012784; 2024 Oct: 0.014678; 2024 Nov: 0.10701; 2024 Dec: 0.11742; 2025 Jan: 0.11742; 2025 Feb: 0.10606; 2025 Mar: 0.021307; 2025 Apr: 0.014205; 2025 May: 0.014678; 2025 Jun: 0.014205 | 0.53977
Project Manager | 2024 Sep: 0.038352; 2024 Oct: 0.044034; 2024 Nov: 0.055871; 2024 Dec: 0.058712; 2025 Jan: 0.087121; 2025 Feb: 0.079545; 2025 Mar: 0.033144; 2025 Apr: 0.028409; 2025 May: 0.029356; 2025 Jun: 0.028409 | 0.48295
Project87
Business Analyst | 2024 Sep: 0.012784; 2024 Oct: 0.014678; 2024 Nov: 0.10701; 2024 Dec: 0.11742; 2025 Jan: 0.11742; 2025 Feb: 0.10606; 2025 Mar: 0.021307; 2025 Apr: 0.014205; 2025 May: 0.014678; 2025 Jun: 0.014205 | 0.53977
Project Manager | 2024 Sep: 0.038352; 2024 Oct: 0.044034; 2024 Nov: 0.055871; 2024 Dec: 0.058712; 2025 Jan: 0.087121; 2025 Feb: 0.079545; 2025 Mar: 0.033144; 2025 Apr: 0.028409; 2025 May: 0.029356; 2025 Jun: 0.028409 | 0.48295
Project88
Business Analyst | 2024 Oct: 0.012784; 2024 Nov: 0.014205; 2024 Dec: 0.080966; 2025 Jan: 0.088068; 2025 Feb: 0.079545; 2025 Mar: 0.088068; 2025 Apr: 0.018939; 2025 May: 0.014678; 2025 Jun: 0.014205; 2025 Jul: 0.014678 | 0.42614
Project Manager | 2024 Oct: 0.051136; 2024 Nov: 0.056818; 2024 Dec: 0.058712; 2025 Jan: 0.058712; 2025 Feb: 0.065814; 2025 Mar: 0.07339; 2025 Apr: 0.044508; 2025 May: 0.044034; 2025 Jun: 0.028883; 2025 Jul: 0.029356 | 0.51136
Project89
Business Analyst | 2024 Nov: 0.012311; 2024 Dec: 0.014678; 2025 Jan: 0.10748; 2025 Feb: 0.10606; 2025 Mar: 0.11742; 2025 Apr: 0.11364; 2025 May: 0.024621; 2025 Jun: 0.014205; 2025 Jul: 0.014678; 2025 Aug: 0.014678 | 0.53977
Project Manager | 2024 Nov: 0.036932; 2024 Dec: 0.044034; 2025 Jan: 0.057292; 2025 Feb: 0.05303; 2025 Mar: 0.08428; 2025 Apr: 0.085227; 2025 May: 0.035038; 2025 Jun: 0.028409; 2025 Jul: 0.029356; 2025 Aug: 0.029356 | 0.48295
Project90
Business Analyst | 2024 Nov: 0.012311; 2024 Dec: 0.014678; 2025 Jan: 0.10748; 2025 Feb: 0.10606; 2025 Mar: 0.11742; 2025 Apr: 0.11364; 2025 May: 0.024621; 2025 Jun: 0.014205; 2025 Jul: 0.014678; 2025 Aug: 0.014678 | 0.53977
Project Manager | 2024 Nov: 0.036932; 2024 Dec: 0.044034; 2025 Jan: 0.057292; 2025 Feb: 0.05303; 2025 Mar: 0.08428; 2025 Apr: 0.085227; 2025 May: 0.035038; 2025 Jun: 0.028409; 2025 Jul: 0.029356; 2025 Aug: 0.029356 | 0.48295
Project91
Business Analyst | 2024 Nov: 0.012311; 2024 Dec: 0.014678; 2025 Jan: 0.10748; 2025 Feb: 0.10606; 2025 Mar: 0.11742; 2025 Apr: 0.11364; 2025 May: 0.024621; 2025 Jun: 0.014205; 2025 Jul: 0.014678; 2025 Aug: 0.014678 | 0.53977
Project Manager | 2024 Nov: 0.036932; 2024 Dec: 0.044034; 2025 Jan: 0.057292; 2025 Feb: 0.05303; 2025 Mar: 0.08428; 2025 Apr: 0.085227; 2025 May: 0.035038; 2025 Jun: 0.028409; 2025 Jul: 0.029356; 2025 Aug: 0.029356 | 0.48295
Project92
Business Analyst | 2025 May: 0.026515; 2025 Jun: 0.16098; 2025 Jul: 0.17614; 2025 Aug: 0.034091; 2025 Sep: 0.028409 | 0.42614
Project Manager | 2025 May: 0.079545; 2025 Jun: 0.11174; 2025 Jul: 0.11742; 2025 Aug: 0.060606; 2025 Sep: 0.056818 | 0.42614
Project93
Business Analyst | 2024 Dec: 0.012784; 2025 Jan: 0.014678; 2025 Feb: 0.074811; 2025 Mar: 0.088068; 2025 Apr: 0.085227; 2025 May: 0.088068; 2025 Jun: 0.018939; 2025 Jul: 0.014678; 2025 Aug: 0.014678; 2025 Sep: 0.014205 | 0.42614
Project Manager | 2024 Dec: 0.051136; 2025 Jan: 0.058712; 2025 Feb: 0.05303; 2025 Mar: 0.058712; 2025 Apr: 0.069602; 2025 May: 0.07339; 2025 Jun: 0.044508; 2025 Jul: 0.044034; 2025 Aug: 0.02983; 2025 Sep: 0.028409 | 0.51136
Project94
Business Analyst | 2025 Jan: 0.012784; 2025 Feb: 0.013258; 2025 Mar: 0.10085; 2025 Apr: 0.11364; 2025 May: 0.11742; 2025 Jun: 0.11364; 2025 Jul: 0.024621; 2025 Aug: 0.014678; 2025 Sep: 0.014205; 2025 Oct: 0.014678 | 0.53977
Project Manager | 2025 Jan: 0.038352; 2025 Feb: 0.039773; 2025 Mar: 0.056345; 2025 Apr: 0.056818; 2025 May: 0.08428; 2025 Jun: 0.085227; 2025 Jul: 0.035038; 2025 Aug: 0.029356; 2025 Sep: 0.028409; 2025 Oct: 0.029356 | 0.48295
Project95
Business Analyst | 2025 Jun: 0.025568; 2025 Jul: 0.16193; 2025 Aug: 0.17614; 2025 Sep: 0.033144; 2025 Oct: 0.029356 | 0.42614
Project Manager | 2025 Jun: 0.076705; 2025 Jul: 0.11458; 2025 Aug: 0.11742; 2025 Sep: 0.058712; 2025 Oct: 0.058712 | 0.42614
Project96
Business Analyst | 2025 Jul: 0.026515; 2025 Aug: 0.11174; 2025 Sep: 0.22348; 2025 Oct: 0.064394; 2025 Nov: 0.028409 | 0.45455
Project Manager | 2025 Jul: 0.10606; 2025 Aug: 0.17235; 2025 Sep: 0.22538; 2025 Oct: 0.12121; 2025 Nov: 0.056818 | 0.68182
Project97
Business Analyst | 2025 May: 0.012784; 2025 Jun: 0.014205; 2025 Jul: 0.080966; 2025 Aug: 0.088068; 2025 Sep: 0.085227; 2025 Oct: 0.088068; 2025 Nov: 0.014205; 2025 Dec: 0.014678; 2026 Jan: 0.014678; 2026 Feb: 0.013258 | 0.42614
Project Manager | 2025 May: 0.051136; 2025 Jun: 0.056818; 2025 Jul: 0.058712; 2025 Aug: 0.058712; 2025 Sep: 0.070549; 2025 Oct: 0.07339; 2025 Nov: 0.042614; 2025 Dec: 0.043561; 2026 Jan: 0.029356; 2026 Feb: 0.026515 | 0.51136
Project98
Business Analyst | 2025 May: 0.012784; 2025 Jun: 0.014205; 2025 Jul: 0.10748; 2025 Aug: 0.11742; 2025 Sep: 0.11364; 2025 Oct: 0.11742; 2025 Nov: 0.014205; 2025 Dec: 0.014678; 2026 Jan: 0.014678; 2026 Feb: 0.013258 | 0.53977
Project Manager | 2025 May: 0.038352; 2025 Jun: 0.042614; 2025 Jul: 0.057292; 2025 Aug: 0.058712; 2025 Sep: 0.08428; 2025 Oct: 0.088068; 2025 Nov: 0.028409; 2025 Dec: 0.029356; 2026 Jan: 0.029356; 2026 Feb: 0.026515 | 0.48295
Project99
Business Analyst | 2025 Oct: 0.028409; 2025 Nov: 0.17045; 2025 Dec: 0.17708; 2026 Jan: 0.029356; 2026 Feb: 0.026515 | 0.43182
Project Manager | 2025 Oct: 0.085227; 2025 Nov: 0.11364; 2025 Dec: 0.11932; 2026 Jan: 0.058712; 2026 Feb: 0.05303 | 0.42992
Timeline: Works in Excel 2013 or higher. Do not move or resize.